## Start Here
Small Business Construction Project Tracker
BizTools · Scalable Essentials · Construction-Contractors Toolbox
THIS WORKBOOK TRACKS ONE JOB
For each new job, choose File ▸ Save As and name the file for that job (e.g., "Johnson-Kitchen.xlsx"). Keep this blank original as your reusable template.
WHAT THIS HELPS YOU DO
Track one construction job from start to finish — budget vs. actual cost, change orders, material readiness, and deadlines — so you can see whether the job is making money and what is about to go wrong, before it costs you.
QUICK START — 4 STEPS
1 | Open the Setup tab and confirm your defaults (target profit margin, retainage %, labor burden).
2 | Enter the job on Job Setup — contract value, dates, and your original budget by category.
3 | Log costs, change orders, and materials on their tabs as they happen — weekly is ideal.
4 | Read your Dashboard. It shows profit, margin, cash, and exactly what to do next.
WHAT THE COLORS MEAN
You type here
Calculated automatically — please don't edit
Section header
▶ Read the How-To Guide (PDF) · Check your business health at BizHealth.ai
Version 3.0 · BizHealth.ai · Not legal, tax, or accounting advice.

## Setup
Setup — Company & Defaults
Fill these once. They power the whole workbook.
YOUR COMPANY
Company name
Owner name
| Currency symbol | $
YOUR DEFAULTS
| Target profit margin % | 15%
| Retainage % held by client | 10%
| Labor burden % | 25%
| "Due soon" window (days) | 7
Tip: these are starting points — change any of them to match how you run your business.
Note on C10: Your goal profit as a % of the contract. Margin = profit ÷ price (NOT markup). 15% is a common floor for small contractors.
Note on C11: The portion a client holds back until the job is finished. 10% is typical. The Dashboard estimates what is being held.
Note on C12: Adds payroll taxes, insurance, and workers' comp on top of base wages. Roughly 20–30% for most trades.
Note on C13: How many days ahead counts as "coming up soon" for deadlines and materials. Default 7 (one week).

## Dashboard
THE BOTTOM LINE
Revised Contract Value | Projected Cost at Completion | Projected Profit
0 | 0 | 0
Projected Margin % | Target Margin | Margin vs. Target (pts)
0% | 15% | 0%
COST & PROGRESS
Total Budgeted Cost | Committed Cost | Actual Cost to Date
0 | 0 | 0
% Complete (cost basis) | Over-Budget Lines | Unbilled Approved COs
0% | 0 | 0
CASH & TIME
Cash Position (this job) | Outstanding to Collect | Retainage Held (est.)
0 | 0 | 0
Days to Deadline | Materials at Risk | Billed to Date
| 0 | 0
WHAT THIS MEANS
Enter your job on Job Setup to begin.
Start by entering your job on the Job Setup tab.

## Job Setup
Job Setup
Enter the job you are tracking. You will see your bid margin instantly.
| THE JOB |  | ORIGINAL BUDGET BY CATEGORY
| Project name |  | Labor
| Client / customer |  | Materials
| Job address |  | Subcontractors
| Contract type | Fixed Price | Equipment
| Start date |  | Permits & Fees
| Target completion |  | Overhead/Other
| Contract value |  | Budgeted total cost | 0
|  |  | Margin at bid | 0%
This is your original estimate — the plan you bid. Track what actually happens on the Cost Tracker.
BILLING & CASH (this job)
Total invoiced to client
Total received
| Retainage held (est.) | 0
| Outstanding to collect | 0
Keep these current so your Dashboard cash position stays accurate.
Note on C15: All progress draws / invoices you have sent the client so far on this job.
Note on C16: Cash actually collected from the client so far.

## Cost Tracker
Cost Tracker
Budget vs. actual for every cost line. Over-budget lines turn red automatically.
| Category | Description | Budget | Committed | Actual | Paid | Variance | % of Budget
Labor
Materials
Subcontractors
Equipment
Permits & Fees
Overhead/Other
| TOTALS |  | 0 | 0 | 0 | 0 | 0
Note on E3: COMMITTED = money you have promised (a signed sub or purchase order) but may not have been invoiced yet.
Note on F3: ACTUAL = cost you have actually been invoiced for. Committed vs. Actual is where owners get blindsided.

## Change Orders
Change Orders
Log every change. The copper number is approved work you have NOT billed yet.
| ⚠ Approved change orders you have NOT billed yet: |  |  |  | 0
| CO # | Date | Description | Value to Client | Cost Impact | Status | Billed?

## Materials
Materials
Track what you need and when. Shortages and backorders flag automatically.
| Item | Supplier | Qty | Needed By | Order Status | On Site? | Flag
Formulas:
Flag = IF([Needed By]="","",IF(OR([Order Status]="Backordered",AND([Needed By]<TODAY(),[On Site?]<>"Yes")),"AT RISK",IF(AND(OR([Order Status]="Not ordered",[Order Status]="Partial",[Order Status]=""),[Needed By]-TODAY()<=Setup!$C13),"WATCH","OK")))

## Schedule
Schedule
Phases and milestones. Past-due phases flag red.
| Phase / Milestone | Planned Start | Planned End | Actual Start | Actual End | % Complete | Status | Days to Planned End
Formulas:
Days to Planned End = IF([Planned End]="","",[Planned End]-TODAY())

## Subs & Vendors
Subs & Vendors
Track balances and paperwork. Paying without a lien waiver flags red.
| Name | Trade | Contract Amount | Paid | Balance | Insurance on File? | Lien Waiver Received? | Flag

## Lists (hidden)
Cost Category | CO Status | Material Status | Phase Status | Invoice Status | Yes/No | Contract Type
Labor | Pending | Not ordered | Not Started | Draft | Yes | Fixed Price
Materials | Approved | Ordered | In Progress | Sent | No | Time & Materials
Subcontractors | Rejected | Partial | Complete | Partially Paid |  | Cost-Plus
Equipment |  | On site |  | Paid
Permits & Fees |  | Backordered
Overhead/Other